## Project
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Create an account | Authentication | Guest | New users can register an account by providing their name, email, and password to access the platform. | Hồng Nguyên | Done | iter1
2 | OTP screen | Authentication | Guest | Users enter a one-time code sent to their email to verify their identity during registration or password recovery. | Hồng Nguyên | Done | iter1
3 | Login/Logout | Authentication | Customer, Staff, Staff Manager | Users can log in using registered credentials and log out to end their session. | Hoàng Minh | Done | iter1
4 | Login with Google | Authentication | Customer, Staff, Staff Manager | Users can log in quickly using their existing Google account. | Quang Minh | Done | iter1
5 | Forgot password | Authentication | Customer, Staff, Staff Manager | Users can request a password reset by entering their registered email to receive a reset link or OTP. | Phong Quyền | Done | iter1
6 | Change password | Account | Customer, Staff, Staff Manager | Users can change their account password by verifying the current one and setting a new one. | Công Minh | Done | iter1
7 | View and Update Profile | Account | Customer, Staff, Staff Manager | Users can view and update personal information, contact details, address, and profile photo (avatar). | Quang Minh | Done | iter1
8 | View Homepage | General | Guest, Customer | Guests and customers can view the homepage to get an overview of the website services and features. |  | Updated | iter1 | iter3
9 | View all motorcycles | General | Guest, Customer | Guests and customers can view a list of all available motorcycles, including photos, rental prices, and basic information. |  | Updated | iter1 | iter2
10 | View a motorcycle in detail | General | Guest, Customer | Guests and customers can view detailed information about a specific motorcycle, including images, specs, price, and included accessories. |  | Updated | iter1 | iter2
11 | View tourism location | Tourism Management | Guest, Customer | Guests and customers can browse suggested tourism destinations with photos, descriptions, and reference links. |  | Done | iter1 | None
12 | View FAQs | FAQ Management | Guest, Customer | Guests and customers can read frequently asked questions and their answers to better understand the service. |  | Done | iter1 | None
13 | View price list | Pricing Management | Guest, Customer | Guests and customers can view the current rental price list for all motorcycle types and rental durations. |  | Updated | iter1 | iter2
14 | View policies | Policy Management | Guest, Customer | Guests and customers can read the platform rental terms and conditions before making a reservation. |  | Done | iter1 | None
15 | Give contact | Contact Management | Guest, Customer | Users can submit a contact form to send questions or requests to the support team. |  | Updated | iter1 | iter2
16 | View event/sales | Promotion Management | Guest, Customer | Guests and customers can view current promotions, discount events, and upcoming campaigns. |  | Done | iter1 | None
17 | Search motorcycles | Search & Recommendation | Guest, Customer | Guests and customers can search and filter motorcycles by brand, category, travel purpose, displacement, or price range. |  | Updated | iter1 | iter3
18 | Get motorcycle suggestions by demand | Search & Recommendation | Guest, Customer | Guests and customers can enter their travel needs such as touring, city riding, or fuel saving to receive suitable motorcycle suggestions from the system. |  | Done | iter1 | None
19 | Contact by chatbot | Chatbot | Guest, Customer | Guests and customers can chat with the system chatbot to get information and rental recommendations from the website. |  | Done | iter1 | None
20 | View booking history | Account | Customer | Customers can view a list of all past and current rental bookings and open any booking to see its full details. |  | Updated | iter2 | iter3
21 | Choose pick up/return date/location | Rental Booking | Customer | Customers can select their preferred pickup and return dates and locations for the motorcycle rental. |  | Updated | iter2 | iter3
22 | Choose motorcycles | Rental Booking | Customer | Customers can browse and select an available motorcycle for their chosen rental period. |  | Updated | iter2 | iter3
23 | Choose accessories | Rental Booking | Customer | Customers can add optional accessories such as helmets or rain gear to their rental order. |  | Updated | iter2 | iter3
24 | Confirm personal information | Rental Booking | Customer | Customers can review and confirm their personal details before proceeding with the booking. |  | Updated | iter2 | iter3
25 | Confirm booking | Rental Booking | Customer | Customers can review the complete booking summary including motorcycle, accessories, dates, and total cost before finalizing. |  | Updated | iter2 | iter3
26 | Make payment | Rental Booking | Customer | Customers can complete payment for their rental booking through available payment methods. |  | Updated | iter2 | iter3
27 | Apply voucher code | Rental Booking | Customer | Customers can enter a voucher or promo code at checkout to receive a discount on their rental. |  | Done | iter2 | None
28 | Cancel booking | Rental Booking | Customer | Customers can submit a cancellation request for an active booking and track the processing status. |  | Done | iter2 | None
29 | Extend booking | Rental Booking | Customer | Customers can request to extend their current rental period by selecting a new return date. |  | Done | iter2 | None
30 | Give rating and feedback | Rental Booking | Customer | Customers can rate the motorcycle and overall service quality after completing a rental. |  | Done | iter2 | None
31 | Add to favorites | Favorite | Customer | Customers can save motorcycles they are interested in to a personal favorites list for easy access when planning a rental. |  | Done | iter2 | None
32 | Get motorcycle suggestions by tourism location | Tourism Management | Customer | Customers can select a tourism destination to receive motorcycle recommendations suitable for that route or terrain. |  | Done | iter2 | None
33 | Manage customer list | Customer Management | Staff | Staff can view, search, and access detailed profiles of all registered customers. |  | Done | iter2 | None
34 | Disable customer account | Customer Management | Staff | Staff can deactivate a customer account that has violated the platform rules. |  | Done | iter2 | None
35 | View overdue rentals | Customer Management | Staff | Staff can view a list of customers who have not returned their motorcycle by the agreed return date. |  | Done | iter2 | None
36 | Advise and consult customer | Customer Management | Staff | Staff can provide consultation to customers regarding motorcycle options, rental pricing, accessories, policies, and active promotions. |  | Done | iter2 | None
37 | Confirm booking | Rental Management | Staff | Staff can review and approve pending booking requests submitted by customers. |  | Updated | iter2 | iter3
38 | Update booking status | Rental Management | Staff | Staff can update the booking status through each rental stage: confirmed → picked up → active → completed. |  | Updated | iter2 | iter3
39 | Cancel booking by staff | Rental Management | Staff | Staff can cancel a booking on behalf of the customer, including providing a reason and processing any applicable refund. |  | Done | iter2 | None
40 | Handle extension request | Extension Management | Staff | Staff can view extension requests submitted by customers and approve or reject them after checking motorcycle availability. |  | Done | iter3 | None
41 | Handle cancellation request | Cancellation Management | Staff | Staff can view cancellation requests submitted by customers and approve or reject them. |  | Done | iter3 | None
42 | CRUD Motorcycle | Motorcycle Management | Staff | Staff can add, update, delete motorcycles and manage their availability status (available, rented, under maintenance, decommissioned). |  | Done | iter3 | None
43 | CRUD price list | Pricing Management | Staff | Staff can add new pricing entries, update existing rental rates, and remove outdated price records. |  | Done | iter3 | None
44 | CRUD FAQs | FAQ Management | Staff | Staff can add new FAQ entries, update existing questions and answers, and remove FAQs that are no longer relevant. |  | Done | iter3 | None
45 | CRUD Tourism Location | Tourism Management | Staff | Staff can add new tourism destinations with photos and descriptions, update existing ones, and remove outdated entries. |  | Done | iter3 | None
46 | CRUD sales/events | Promotion Management | Staff | Staff can create new promotions or events with voucher codes, update active campaigns, and remove expired ones. |  | Done | iter3 | None
47 | CRUD accessories | Accessory Management | Staff | Staff can add new accessories, update stock and pricing information, and remove accessories that are no longer available. |  | Done | iter3 | None
48 | View customer feedback and contact | Feedback Management | Staff | Staff can view ratings and reviews from customers after completed rentals, and read contact form submissions sent by customers. |  | Done | iter3 | None
49 | Track rental motorcycle GPS location | Rental Management | Staff | Staff can view the real-time GPS location of motorcycles currently being rented on an interactive map. |  | Done | iter3 | None
50 | Manage staff list | Staff Management | Staff Manager | The manager can view, search, and access detailed profiles of all staff accounts along with their roles and permissions. |  | Done | iter3 | None
51 | Disable staff account | Staff Management | Staff Manager | The manager can deactivate a staff account to revoke system access when needed. |  | Done | iter3 | None
52 | Manage staff roles and permissions | Staff Management | Staff Manager | The manager can assign or update roles and access permissions for staff members in the system. |  | Done | iter3 | None
53 | View dashboard | Dashboard & Analytics | Staff Manager | The manager can view a dashboard showing key metrics such as active rentals, revenue, motorcycle availability, and booking statistics. |  | Done | iter3 | None
54 | View rental analytics report | Dashboard & Analytics | Staff Manager | The manager can view reports on motorcycle rental performance, including most and least rented vehicles, demand trends, and discount recommendations. |  | Done | iter3 | None
Effort Distribution
No | Full name | Student ID | Effort (%)
1 | Lê Quang Minh | DE190071 | 0%
2 | Lê Quang Minh | DE190071 | 0%
3 | Lê Quang Minh | DE190071 | 0%
4 | Lê Quang Minh | DE190071 | 0%
5 | Lê Quang Minh | DE190071 | 0%

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Create an account | Authentication | New users can register an account by providing their name, email, and password to access the platform. | Hồng Nguyên | Done
2 | OTP screen | Authentication | Users enter a one-time code sent to their email to verify their identity during registration or password recovery. | Hồng Nguyên | Done
3 | Login/Logout | Authentication | Users can log in using registered credentials and log out to end their session. | Hoàng Minh | Done
4 | Login with Google | Authentication | Users can log in quickly using their existing Google account. | Quang Minh | Done
5 | Forgot password | Authentication | Users can request a password reset by entering their registered email to receive a reset link or OTP. | Phong Quyền | Done
6 | Change password | Account | Users can change their account password by verifying the current one and setting a new one. | Công Minh | Done
7 | View and Update Profile | Account | Users can view and update personal information, contact details, address, and profile photo (avatar). | Quang Minh | Done

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View Homepage | General | Guests and customers can view the homepage to get an overview of the website services and features. | All of us | Updated | Done | Done
2 | View all motorcycles | General | Guests and customers can view a list of all available motorcycles, including photos, rental prices, and basic information. |  | Updated | Done | Done
3 | View a motorcycle in detail | General | Guests and customers can view detailed information about a specific motorcycle, including images, specs, price, and included accessories. |  | Updated | Done | Done
4 | View tourism location | Tourism Management | Guests and customers can browse suggested tourism destinations with photos, descriptions, and reference links. |  | Done | Done | Done
5 | View FAQs | FAQ Management | Guests and customers can read frequently asked questions and their answers to better understand the service. |  | Done | Done | Done
6 | View price list | Pricing Management | Guests and customers can view the current rental price list for all motorcycle types and rental durations. |  | Updated | Done | Done
7 | View policies | Policy Management | Guests and customers can read the platform rental terms and conditions before making a reservation. |  | Done | Done | Done
8 | Give contact | Contact Management | Users can submit a contact form to send questions or requests to the support team. |  | Updated | Done | Done
9 | View event/sales | Promotion Management | Guests and customers can view current promotions, discount events, and upcoming campaigns. |  | Done | Done | Done
10 | Search motorcycles | Search & Recommendation | Guests and customers can search and filter motorcycles by brand, category, travel purpose, displacement, or price range. |  | Updated | Done | Done
11 | Get motorcycle suggestions by demand | Search & Recommendation | Guests and customers can enter their travel needs such as touring, city riding, or fuel saving to receive suitable motorcycle suggestions from the system. |  | Done | Done | Done
12 | Contact by chatbot | Chatbot | Guests and customers can chat with the system chatbot to get information and rental recommendations from the website. |  | Done | Done | Done
13 | View booking history | Account | Customers can view a list of all past and current rental bookings and open any booking to see its full details. |  | Updated | Done | Done
14 | Choose pick up/return date/location | Rental Booking | Customers can select their preferred pickup and return dates and locations for the motorcycle rental. |  | Updated | Done | Done
15 | Choose motorcycles | Rental Booking | Customers can browse and select an available motorcycle for their chosen rental period. |  | Updated | Done | Done
16 | Choose accessories | Rental Booking | Customers can add optional accessories such as helmets or rain gear to their rental order. |  | Updated | Done | Done
17 | Confirm personal information | Rental Booking | Customers can review and confirm their personal details before proceeding with the booking. |  | Updated | Done | Done
18 | Confirm booking | Rental Booking | Customers can review the complete booking summary including motorcycle, accessories, dates, and total cost before finalizing. |  | Updated | Done | Done
19 | Make payment | Rental Booking | Customers can complete payment for their rental booking through available payment methods. |  | Updated | Done | Done
20 | Apply voucher code | Rental Booking | Customers can enter a voucher or promo code at checkout to receive a discount on their rental. |  | Done | Done | Done
21 | Cancel booking | Rental Booking | Customers can submit a cancellation request for an active booking and track the processing status. |  | Done | Done | Done
22 | Extend booking | Rental Booking | Customers can request to extend their current rental period by selecting a new return date. |  | Done | Done | Done
23 | Give rating and feedback | Rental Booking | Customers can rate the motorcycle and overall service quality after completing a rental. |  | Done | Done | Done
24 | Add to favorites | Favorite | Customers can save motorcycles they are interested in to a personal favorites list for easy access when planning a rental. |  | Done | Done | Done

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Get motorcycle suggestions by tourism location | Tourism Management | Customers can select a tourism destination to receive motorcycle recommendations suitable for that route or terrain. |  | Done | Done | Done
2 | Manage customer list | Customer Management | Staff can view, search, and access detailed profiles of all registered customers. |  | Done | Done | Done
3 | Disable customer account | Customer Management | Staff can deactivate a customer account that has violated the platform rules. |  | Done | Done | Done
4 | View overdue rentals | Customer Management | Staff can view a list of customers who have not returned their motorcycle by the agreed return date. |  | Done | Done | Done
5 | Advise and consult customer | Customer Management | Staff can provide consultation to customers regarding motorcycle options, rental pricing, accessories, policies, and active promotions. |  | Done | Done | Done
6 | Manage booking list | Rental Management | Staff can view all rental bookings and open any booking to review its complete details. |  | Updated | Done | Done
7 | Confirm booking | Rental Management | Staff can review and approve pending booking requests submitted by customers. |  | Done | Done | Done
8 | Update booking status | Rental Management | Staff can update the booking status through each rental stage: confirmed → picked up → active → completed. |  | Done | Done | Done
9 | Cancel booking by staff | Rental Management | Staff can cancel a booking on behalf of the customer, including providing a reason and processing any applicable refund. |  | Done | Done | Done
10 | Handle extension request | Extension Management | Staff can view extension requests submitted by customers and approve or reject them after checking motorcycle availability. |  | Done | Done | Done
11 | Handle cancellation request | Cancellation Management | Staff can view cancellation requests submitted by customers and approve or reject them. |  | Done | Done | Done
12 | CRUD Motorcycle | Motorcycle Management | Staff can add, update, delete motorcycles and manage availability status (available, rented, under maintenance, decommissioned). |  | Done | Done | Done
13 | CRUD price list | Pricing Management | Staff can add new pricing entries, update existing rental rates, and remove outdated price records. |  | Done | Done | Done
14 | CRUD FAQs | FAQ Management | Staff can add new FAQ entries, update existing questions and answers, and remove FAQs that are no longer relevant. |  | Done | Done | Done
15 | CRUD Tourism Location | Tourism Management | Staff can add new tourism destinations with photos and descriptions, update existing ones, and remove outdated entries. |  | Done | Done | Done
16 | CRUD sales/events | Promotion Management | Staff can create new promotions or events with voucher codes, update active campaigns, and remove expired ones. |  | Done | Done | Done
17 | CRUD accessories | Accessory Management | Staff can add new accessories, update stock and pricing information, and remove accessories that are no longer available. |  | Done | Done | Done
18 | View customer feedback and contact | Feedback Management | Staff can view ratings and reviews from customers after completed rentals, and read contact form submissions sent by customers. |  | Done | Done | Done
19 | Track rental motorcycle GPS location | Rental Management | Staff can view the real-time GPS location of motorcycles currently being rented on an interactive map. |  | Done | Done | Done
20 | Manage staff list | Staff Management | The manager can view, search, and access detailed profiles of all staff accounts along with their roles and permissions. |  | Done | Done | Done
21 | Disable staff account | Staff Management | The manager can deactivate a staff account to revoke system access when needed. |  | Done | Done | Done
22 | Manage staff roles and permissions | Staff Management | The manager can assign or update roles and access permissions for staff members in the system. |  | Done | Done | Done
23 | View dashboard | Dashboard & Analytics | The manager can view a dashboard showing key metrics such as active rentals, revenue, motorcycle availability, and booking statistics. |  | Done | Done | Done
24 | View rental analytics report | Dashboard & Analytics | The manager can view reports on motorcycle rental performance, including most and least rented vehicles, demand trends, and discount recommendations. |  | Done | Done | Done